# Test Plan Document Template

## Introduction

##### This appendix contains a template for a Test Plan document, guidance on its use, and where appropriate, examples of the typical contents of such a document.  This template may be used as the basis of a Test Plan document for a particular test phase.

##### As described in Chapter 4 (The Management and Planning of Testing), each testing project must generate a Test Plan as one of the documents produced prior to the commencement of the testing activities.

##### Where text appears within the body of the template in angle brackets (< >), this denotes a place marker, which must be replaced with the appropriate information for a particular testing phase.

##### Text that appears in italic type is provided for information only (such as illustrative examples), and should not appear in the final Test Plan document.

##### Where references to “Appendices” appear within this appendix, these refer to other appendices in this book.  The term “Annex” is used to refer to supplementary sections within this template.

##### The principal approach to be used in writing a Test Plan Document is to keep it brief and simple.  Make best use of the supporting information presented in this book (such as the other relevant template appendices), as well as pertinent material from the appropriate testing phase chapters.

##### Test Plan Document Front Sheet

| ##### Document Information {to <Client> Doc Standard} |  |
| --- | --- |
| ##### Project ID: | ##### <Project ID> The unique ID for this testing project |
| ##### Document Ref: | ##### <Doc Ref> A unique document reference for this document |
| ##### Testing Phase: | ##### <Testing Phase> The testing phase (e.g., Unit test) |
| ##### AUT Title: | ##### <AUT Title> The definitive title of the application under test |
| ##### Date: | ##### <Date> The date this document was completed |

| ##### Distribution |  |
| --- | --- |
| ##### Copy Number | ##### Recipient |
| ##### 1. | ##### <activity leader> That is, Development Team Leader for Unit and Integration Testing, Test Team Leader for System Test, etc. |
| ##### 2. | ##### <Test Analyst> i.e. the person designing and developing the Test Cases |
| ##### N. | ##### Project File |

| ##### Review & Approval |  |
| --- | --- |
| ##### Issue: | ##### <Issue status> Issue status of the document (e.g. Draft, v1.0) |
| ##### R&A Number: | ##### <R&A reference> The reference to the final approving review |
| ##### Author | ##### <name of the author> The person who wrote this document |
| ##### Author Signature | ##### <signature of author> |
| ##### Approval (PM) | ##### <name of the Project Manager> |
| ##### Approval (PM) Signature | ##### <signature of the Project Manager > |
| ##### Approval (QA) | ##### <name of the Quality Assurance representative> |
| ##### Approval (QA) Signature | ##### <signature of the Quality Assurance representative> |

##### Contents

##### 1	Introduction

##### 1.1	Background

##### 1.2	Structure of the Document

##### 1.3	References

##### 2	Test Approach and Constraints

##### 2.1	Introduction

##### 2.2	Test Objectives

##### 2.3	Test Constraints

##### 3	Risks and Dependencies

##### 3.1	Introduction

##### 3.2	Risks

##### 3.3	Dependencies

##### 4	Test Assumptions and Exclusions

##### 4.1	Introduction

##### 4.2	Assumptions

##### 4.3	Exclusions

##### 5	Entry and Exit Criteria

##### 5.1	Introduction

##### 5.2	Entry Criteria

##### 5.3	Exit Criteria

##### 6	Testing Project Controls

##### 6.1	Introduction

##### 6.2	Roles and Responsibilities

##### 6.3	Training Requirements

##### 6.4	Problem Reporting

##### 6.5	Progress Reporting

##### Annex A – Test Plan

##### 1	Introduction

##### 1.1	Background

This document provides the plan for completing the testing activities required for the <Testing Phase> testing of the <AUT Title>.

This section should contain a brief background and history to this testing project which should include:

a)	a brief description of the purpose of the AUT

b)	definitive version information for the AUT

c)	any other relevant supporting information.

##### 1.2	Structure of the Document

##### This document is structured in the following manner:

##### a)	Chapter 2 describes the approach to testing including the objectives of the project and any constraints

##### b)	Chapter 3 describes the risks and dependencies associated with the testing project

##### d)	Chapter 4 lists the test assumptions and exclusions

##### e)	Chapter 5 documents the entry and exit criteria for testing

##### f)	Chapter 6 lists the project controls to be employed in the testing project

##### h)	Annex A provides a <type of plan> plan of the testing project {such as a Man Power and Milestone plan or a Gantt Chart.  If a Project Management or Planning tool is being used on the project, it may be possible to obtain a hard copy of the plan to insert into the Annex}.

##### 1.3	References

##### A numbered list of documents referenced within this document.  For example, <list of references to Overall Project Documents>

##### 1)	<Project authorisation document>

##### 2)	<Overall Project Plan>

##### 3)	<Quality Assurance Plan>

##### 4)	<Configuration Management Plan>

##### 5)	<Relevant Policies referenced within this document>

##### 6)	<Relevant Standards referenced within this document>

##### <list of references to items specific to this testing project>

##### 7)	<AUT Title> Functional Specification (version N.N), <date>

##### 8)	<AUT Title> Design Specification (version N.N), <date>

##### 9)	<AUT Title> Users Guide (version N.N), <date> (if appropriate)

##### 10)	<AUT Title> Operations Guide (version N.N), <date> (if appropriate)

##### 11)	<AUT Title> Installation Guide (version N.N), <date> (if appropriate).

##### 2	Test Approach and Constraints

##### 2.1	Introduction

##### This chapter describes the overall approach that will be used in testing the AUT and any constraints that may apply.  These will be used at a high level to support the planning of the testing project.

##### This chapter also documents the use of any particular testing tool (such as an automated record/playback tool) and its details (version number, release information, etc.), or project support tool (such as a project planning or project metrics tools).

##### 2.2	Test Objectives

##### This section lists the high level objectives of the testing project.  For example, in Regression Testing a particular AUT, the objectives might include  - “the Regression Testing process will specifically consider just the functionality of the AH51 module modified during the extensions to the system, and any interfaces between this module and other related modules”.

##### It will also be appropriate to list any exclusions.  For example, in Regression Testing a particular AUT, the objectives might include  - “the Regression Testing will not address any load or performance issues”.

##### 2.3	Test Constraints

##### This section lists any constraints that may apply to the testing project.  For example, in Regression Testing a particular AUT, the objectives might include  - “Regression Testing must be complete (including correction of errors and retesting) by the Nth of October 2005 for scheduled release to beta test client site”.

##### 3	Risks and Dependencies

##### 3.1	Introduction

##### This chapter documents the risks and dependencies that apply to this testing project.  These will be used at a high level to support the planning of the testing project.

##### 3.2	Risks

##### This section documents risks that may have a deleterious impact on the testing project.  The occurrence, impact and likelihood of these risks must be reviewed during the course of the testing project, and procedures for mitigation/recovery must be documented.

##### The level of rigor employed in the process of identifying risks will depend on a number of factors, including:

##### a)	the business criticality of the AUT

##### b)	safety criticality of the AUT

##### c)	whether the AUT is to be used in-house or supplied to a client.

##### Although typically the process of identifying risks to the testing project is conducted in an informal manner, relying on the experience of the testing staff (and in particular the Test Team Leader/Development Leader), a number of tools and methods are available (see Reference 11 (of this book) for example).

##### For example, in Regression Testing a particular AUT, the following risk might have been identified  - “It is possible that the latest version of the operating system that was planned to be used for testing the AUT will not be available from the manufacturer in time for the planned testing start date.  In the event that this occurs, testing will proceed using the current version of the operating system software, with a sub-set of Regression Tests to be rerun as and when the new version of the operating system becomes available”.

##### 3.3	Dependencies

##### This section documents any events that must take place as a prerequisite to any of the planned events within the testing project.  The progress of these dependencies must be reviewed during the course of the testing project to determine their impact on the testing project timescales.

##### Dependencies can be categorized as:

##### a)	internal - that is, a dependency originating within the testing project.

##### b)	external - that is, a dependency originating outside of the testing project.

##### For example, in Regression Testing a particular AUT, an internal dependency might be “The start of the testing process by the Tester is dependant on receipt of the Test Script and Test Cases from the Test Analyst.”

##### An external dependency might be “The testing start date is dependant on the delivery by the software development team of version N.N of the AUT.”

##### 4	Test Assumptions and Exclusions

##### 4.1	Introduction

##### This chapter provides greater detail about the testing process and in particular the assumptions that have been made for the purposes of the testing project, precisely what issues will be addressed by the testing, and what issues will not be addressed.

##### 4.2	Assumptions

##### This section lists the assumptions that have been made for the purposes of the testing project.  It also lists the specific aspects of the AUT to be tested.

##### For example, in Regression Testing a particular AUT, the following assumptions have been made:

##### a)	The testing project will test:

##### - the functionality of the AH51 module

##### - the interface between module AH51 and AH52

##### - the interface between module AH51 and AH53

##### b)	The database server will be live during the entirety of the testing process

##### c)	Access will be available to the test rig outside of normal working hours.

##### 4.3	Exclusions

##### This section lists the items not to be included in the testing project.

##### For example, in Regression Testing a particular AUT, the following exclusions have been made:

##### a)	The testing project will not test:

##### - performance aspects of the AH51 module

##### - load aspects of the AH51 module

##### - the interface between the AH51 module and the AH50 module

##### b)	It is not necessary for a User Representative to be present during testing

##### c)	Testing tool support will not be necessary for this testing project.

##### 5	Entry and Exit Criteria

##### 5.1	Introduction

##### This chapter documents the criteria that must be satisfied before testing can begin as well as the criteria to be satisfied in order for testing to finish.  This information is recorded to provide a clear and unambiguous means of determining when to start or stop testing.

##### 5.2	Entry Criteria

##### This section lists the entry criteria for the testing project.

##### For example, in Regression Testing a particular AUT, the following entry criteria have been specified:

##### a)	The test environment has been set up (and tested)

##### b)	The amended (to reflect changes to the AUT) Requirements Specification document has been received

##### b)	The final copy of the amended AUT has been received from the Development Team and has been installed on the test environment

##### c)	The latest version of the operating system required for testing has been installed on the test environment

##### d)	The test project has been appropriately resourced.

##### 5.3	Exit Criteria

##### This section lists the exit criteria for halting the testing process.

##### For example:

##### a)	no outstanding defects

##### b)	observed defects are below an agreed-on profile, such as:

##### -	no critical defects, and less than N severe defects

##### -	N hours testing time without observing a defect

##### -	a complete run (or rerun) through the test script with no defects

##### c)	some budgetary criterion, such as:

##### -	the assigned testing budget has been exceeded

##### -	the assigned testing effort had been exceeded

##### d)	some scheduling criterion, such as:

##### -		testing must stop to allow planned delivery of AUT

##### -		testing must stop to allow planned development of AUT (e.g., Unit testing must be complete by a certain date to allow integration of the AUT to begin)

##### e)	testing must stop because the AUT is unfit for this level of testing, that is, the AUT is of such poor quality that further testing would be a waste of effort.

##### 6	Testing Project Controls

##### 6.1	Introduction

##### This chapter documents the staff members involved in the testing project and their roles and responsibilities.  It also describes the manner in which problems and progress will be reported.

##### The precise details for each of the following sections will need to be tailored to match the particular testing phase (see appropriate testing phase chapter of this book) and the specific testing requirements for the AUT (see Test Specification Document, Appendix D).

##### 6.2	Roles and Responsibilities

##### This section specifies the names, roles and responsibilities of the staff involved in the testing project.

##### For example, for a System Testing project, the following roles would need to be documented:

##### a)	Test Team Leader - Carol Jenkins

##### b)	Test Analyst - Martin Stemp

##### c)	Tester - Chris Dodsworth

##### d)	User Representative - Angela Jones

##### e)	Independent Test Observer - Lesley Williams.

##### 6.3	Training Requirements

##### This section documents any particular training needs for the staff involved in the testing.

##### For Example, the Test Analyst and Tester may require training with the AUT to gain the familiarity with the user interface to improve their effectiveness during the design and execution of the tests.

##### 6.4	Problem Reporting

##### This section documents the manner in which defects observed during testing are recorded and reported to the appropriate staff.

##### For example, all defects observed during System Testing will be recorded on the appropriate Test Result Record Form (see Appendix F).  All such defects will be reviewed during the Post Test Review Meeting, where the Test Team Leader and the Development Team Leader will discuss the scope of remedial work to the AUT, timescales for correction, and any test case(s) that need to be rerun as a result of the remedial work”.

##### If a test-management tool or a defect-reporting tool is being used within a particular testing project, the tool details and the process by which it will be used should also be documented here.

##### 6.5	Progress Reporting

##### This section documents the frequency, scope and detail of testing project progress reporting and describes the staff involved in the process.

##### For example, the Test Team Leader will issue a weekly progress report.  This report will include:

##### a)	planned verses actual progress

##### b)	revised estimates and their justification

##### c)	any outstanding problems and issues.

##### The report will be issued to:

##### a)	the Testing Manager

##### b)	Test Analyst

##### c)	Tester

##### d)	Independent Test Observer.

##### The Test Team Leader will convene a progress meeting every other week to report on the testing project progress.  The following staff should be invited:

##### a)	Testing Manager

##### b)	Development Team Leader

##### c)	the User Representative

##### d)	the Independent Test Observer.

##### A 	Test Plan

##### This annex contains a <type of plan> plan of the testing project {such as a Man Power and Milestone plan or a Gantt Chart.  If a Project Management or Planning tool is being used on the project, it may be possible to obtain a hard copy to insert into the Annex}.

##### As a minimum, the <type of plan> should include the following items:

##### 1)	task names

##### 2)	timescales for each task and milestones

##### 3)	risks and dependencies

##### 4)	brief deliverable names

##### The V Model (Chapter 4) can be used to provide useful guidance during the planning aspects of the testing project.